## Sheet1
Airport Door Activation & Access Control Checklist
Status | DesignPhase
DEFINE DOOR FUNCTIONALITY
| Owner intent established | Key / Card / Passage / Push Btn
| Access type confirmed | Single / Dual reader
Review design and submittals
Hardware & REX Configuration
Hardware matches intent
REX type installed (eye/button/integral)
Signage & Room Naming/Numbering
Owner approve room nomenclature
Regulatory signage identified
ADA signage identified
Life Safety signage identified
Door numbering scheme
| Door numbering consistency | Maintain design numbering or modify for existing formats
Operational Phase
| Core Transition & Keying | Consistency with legacy & new facilities
Key and Core delivery address and owner POC.
| Construction cores removed | Clear any latch blocks or shunting
Knox box coordination
Checklist for construction - owner core change
Owner core installed
Keying hierarchy confirmed
Access Control Programming
| Card reader online | network operational
Maintain SSI in email and notes
| Access groups assigned | Coordinate trial/testing for all access groups
Access groups programmed
| Pushbutton code programmed | Document code change cycle
Time zones and open hours configured
Programming limited access paths for employee screening
Functional Testing
Mechanical operation
| Authorized access confirmed | Coordinate trial/testing for all authorized groups
| Door alarm shunting process | PBBs and other public access needs
Hold open timing
Door Stops and Magnetic Holds
Astragal Function
Coordinator Function
Unauthorized access denied
REX operational
Breach alarm triggers
Hold-open alarm triggers
Coordinate camera views and pop-ups
| ADA open force test | Maximum 5 pounds
Final Inspection & Documentation
Final cleaning complete
Obstructions cleared
Door functionality and smooth operation
| All documents submitted | Schedules, drawings, checklist, key matrix
Owner acceptance received